## Work-in-progress forecast - cur
FormNo | Publication title | Date originally published | Current version date | Current (or last) version number | Notes | Last confirmed (or withdraw or archive) date | Date of next scheduled review (Forecasted date) | Members only | BSIA Responsible | Section responsible | Work in progress | Subject to updating | Form status | Website URL
173 | Access Control Systems and Disability Discrimination – A guide | 2004-12-31 | 2015-03-01 | 3.1 | Review meeting 10/01. 23/1 - GE has been working on this - will go to Section this week. 5/1 - with SL for checking. 06/02 - KAH has proof read, with GE for amending. 06/02 - KAH has proof read. With GE for amending. 20/2 - GE | 2016-03-01 | 2025-05-31 | No | GE | AAP | Yes | Yes | Revise-review-new-publication (WIP)
258 | Joining the BSIA | 2019-03-01 | 2019-03-01 |  | 23.01.25 - GE had form, forwarded to Maz to ask Paddy for an update. 29.01.25 Form now sent to Paddy, Maz now awaiting response from Paddy. 12.02.25 Paddy advised Form to be reviewed and updated by Tech Team. 12.02.25 - PK advised form in dire need o | 2019-03-01 | 2025-04-30 | No | Membership | BSIA | Yes | Yes | Revise-review-new-publication (WIP)
266 | Why choose a BSIA member - - NEW TITLE ISSUED (How Professional Security Protects Your World) | 2009-07-01 | 2009-07-01 |  | 14/5- Need an update from LB 15/05 PK working on this over next couple of months - will form part of an education piece to support the Project Research fund, which hasn't been signed-off yet. 29/05 - with PK. 18/06 - still with PK, | 2016-07-20 | 2025-05-30 | No | Membership | BSIA | Yes | Yes | Revise-review-new-publication (WIP)
347 | Artificial IntelligenceAutomatic Facial Reconition - Ethical usage | 2021-01-01 | 2021-01-01 | 1 | 18/06/24 - Agreed to start the review of this guide following the publication of BS 9347. 02/09 - Going to be discussed in the next SIG meeting 02.10.24. 27/09 GE to be discussed in the next SIG Meeting with the new Cha | 2021-01-01 | 2025-05-30 | No | GE | VSS | Yes | Yes | Revise-review-new-publication (WIP)
369 | CySPAG Essentials Installers scheme Cybersecurity 10 point plan | 2024-02-19 | 2024-02-19 |  | 14/05 - Draft complete awaiting final input from stakeholders & CySPAG. 29/05: Review complete awaiting PK and MR to move it forward. 18/06/24 - Document is complete - Glenn disputing reference to CBs, MR chasing response | 2024-05-30 | 2025-04-14 | No | GE | CySPAG | Yes | Yes | Revise-review-new-publication (WIP)
370 | CySPAG Essentials Installers scheme Cybersecurity 10 point plan - registration document | 2024-06-12 | 2024-06-12 |  | 18/06/24 - creatiing a new registration process document for use with the CySPAG Essentials 10 point cyber scheme. Its use will be to explain to scheme holders (NSI/SSAIB/CySPAG) how the scheme will be administered. 01/07 - O | 2024-07-10 | 2025-04-14 | No | MR | CySPAG | Yes | Yes | Revise-review-new-publication (WIP)
375 | Security equipment manufacturer’s UK scheme for I&HAS standards |  |  |  | 21.02.25 - Resurrected from early 2024 following discussions for potential inclusion in the NPCC SSG policy for April 2025. Reshared the latest draft (with MA comments) to SEMS members and request input from them to update th | 2024-01-04 | 2025-04-30 | No | MR | SEMS | Yes | Yes | Revise-review-new-publication (WIP)
376 | Video Surveillance Systems standards Catalogue | [5 empty] | 2025-04-30 |  | GE | VSS | Yes | Yes | Revise-review-new-publication (WIP)